## Cover page
SME Guideline templates
consolidated templates for SME Guideline
Template title | Guideline Figure | Guideline Chapter | Link
Turtle Diagram PM | 4 | 3.2.3 | Link
Turtle Diagram RM | 5 | 3.2.3 | Link
Contigency plan | 6 | 3.2.4 | Link
Inspection report | 7 | 3.2.6 | Link
Competency matrix | 8 | 3.2.7 | Link
Documented information | 9 | 3.2.8 | Link
Transfer plan | 10 | 3.2.9 | Link
Change management register | 11 | 3.2.12 | Link
Requirements tracebility matrix | 12 | 3.2.13 | Link
Supplier fact sheet | 16 | 3.2.15 | Link
Production readiness | Table: 3 | 3.2.16 | Link
Manufacturing quality control plan | 18 | 3.2.19 | Link
First article inspection | 19 | 3.2.22 | Link
Audit program | 20 | 3.2.25 | Link
Process review report | 21 | 3.2.26 | Link
FMEA | - | - | Link

## 4 Turtle Diagram PM
Turtle Diagram | [6 empty] | Turtle instructions:
10 internal/external process supplier |  | 1 Material Resources / Infrastructure (With What?) | 2 Process Owner | 3 Personal Resources (With Who?) |  | 11 internal/external process customer | Item-Nr. | Description
|  | ERP System (SAP) | Process Owner: Mr. XY | Cross functional PM team: |  |  | 1 | Identify the most relevant Material Resources, e. g.
|  | MS Office | Process Manager: Mrs. YZ | Project manager |  |  |  | · buildings and associated utilities
|  | MS Project |  | Commercial project manager |  |  |  | · equipment, including hardware and software
|  | Primavera |  | Project procurement manager |  |  |  | · transportation resources
|  |  |  | Engineering |  |  |  | · information and communication technology
|  |  |  | Quality manager in project |  |  | 2 | Identify the responsible process owner (function and name)
[7 empty] | 3 | Identify the most relevant participants / roles involved in the process
[7 empty] | 4 | Identify the most relevant inputs, e. g.
· results of preceding processes
· external requirements
· internal requirements
· laws, standards und regulations
· raw materials
| external: | 4 Input (What Do We Receive?) |  | 6 Output (What Do We Deliver?) | external: |  | 5 | Identify the process incl. Process steps
| Customer | Inquiry documents |  | Project Management plan | Customer |  | 6 | Identify the most relevant outputs, e. g.
| Operator | Technical & commercial specifications |  | Project Gantt | Operator |  |  | · product / service (in compliance with input requirements)
|  | Customer requirements |  | Project docuemnts | Assessor |  |  | · documentation (e. g. product documentation, reports, test protocols)
| internal: | Legal requirements |  | Product delivery according time and quality |  |  | 7 | Identify the most relevant work content / process operation, e. g.
| Sales |  |  | Fullfillment of all requirements | Internal |  |  | · procedures
|  |  |  | Leassons learned report | Requirements management |  |  | · instructions
[5 empty] | Engineering |  |  | · methods
[5 empty] | Procurement |  | 8 | Identify the most relevant risks and opportunities
[5 empty] | Manufacturing |  | 9 | Identify the performance indicators most relevant to customers / product quality
[7 empty] | 10 | Identify the internal/external suppliers
[7 empty] | 11 | Identify the internal/external customers
|  | 7 Work Content / Process Operation (How?) | 8 Main Risks & Opportunities | 9 Performance Indicators (How Many?)
|  | Project management guidelines | Risks: | On time delivery
|  | Working & process procedures | Technical issues | Non-conformities raised by the customer
|  |  | Lack of resources | Project Costs
Adherence to milestones
Degree of milestone fullfilment
|  |  | Opportunities | Customer satisfaction
|  |  | Gain more contracts | Quality deficiency costs
Good customer relationship / customer satisfaction
Process
Project Management
-Project Planning, Executing,Monitoring & Controlling, Closing.

## 5 Turtle Diagram RM
Turtle Diagram | [6 empty] | Turtle instructions:
10 internal/external process supplier |  | 1 Material Resources / Infrastructure (With What?) | 2 Process Owner | 3 Personal Resources (With Who?) |  | 11 internal/external process customer | Item-Nr. | Description
|  | ERP System (SAP) | Process Owner: Mr. XY | Cross functional PM team: |  |  | 1 | Identify the most relevant Material Resources, e. g.
|  | MS Office | Process Manager: Mrs. YZ | Project Manager |  |  |  | · buildings and associated utilities
|  | Microoft DOORS |  | Commercial project manager |  |  |  | · equipment, including hardware and software
|  | Polarion® REQUIREMENTS™ |  | Requirements manager |  |  |  | · transportation resources
|  |  |  | Requirements engineer |  |  |  | · information and communication technology
|  |  |  | Quality manager in Project |  |  | 2 | Identify the responsible process owner (function and name)
|  |  |  | Homologation manager |  |  | 3 | Identify the most relevant participants / roles involved in the process
[7 empty] | 4 | Identify the most relevant inputs, e. g.
· results of preceding processes
· external requirements
· internal requirements
· laws, standards und regulations
· raw materials
| external: | 4 Input (What Do We Receive?) |  | 6 Output (What Do We Deliver?) | external: |  | 5 | Identify the process incl. Process steps
| Customer | Tender / Contract |  | List of compliance (requirements) | Customer |  | 6 | Identify the most relevant outputs, e. g.
| Operator | Feasibility Analysis |  | Requirements & Design specification | Operator |  |  | · product / service (in compliance with input requirements)
|  | Customer requirements / requirements specification |  | Validation & verification reports | Assessor |  |  | · documentation (e. g. product documentation, reports, test protocols)
| internal: | Product requirements |  |  |  |  | 7 | Identify the most relevant work content / process operation, e. g.
| Sales | Legal requirements |  |  | Internal |  |  | · procedures
| Project Team | Norms / Standards |  |  | Sales |  |  | · instructions
| Product Manager | Market research |  |  | Project Manager |  |  | · methods
|  | Homologation requirements |  |  | Product Manager |  | 8 | Identify the most relevant risks and opportunities
|  | Serviceability requirements |  |  | Developement Project |  | 9 | Identify the performance indicators most relevant to customers / product quality
[7 empty] | 10 | Identify the internal/external suppliers
[7 empty] | 11 | Identify the internal/external customers
|  | 7 Work Content / Process Operation (How?) | 8 Main Risks & Opportunities | 9 Performance Indicators (How Many?)
|  | Project guidelines | Risks: | % of assed requirements
|  | Working procedures | Technical issues | % of requirements with risk
|  | Requirements management process prcedure | Lack of resources (Time & manpower) | % of non-compliant requirements
Oversight of relevant requirements
Incorrect evaluation of requirements
Opportunities
Gain more contracts
Good customer relationship / customer satisfaction
Avoiding quality defiency costs
Process
Requirements management
Requirements identification, analysis, specification
& validation

## 6 Contingency plan
Contingency Plan
Submitted by: |  |  | Date submitted:
Reviewed by: |  |  | Date reviewed:
ID | Event | Likelihood | Impact | Score | Solution to deal with event | Responsible
LOW / MEDIUM / HIGH
1 | Equipment breakdown | 2 | 3 | 6 | Inform supervisor of the shift. A first repar approach is given by supervisor and operators. Supervisor informs to maintencance in case of an unrepairable breakdown | Mr. Xing. Tel. 176 879 4444 xing@example.com
2 | Missing parts in production line due to not any material in stock | 1 | 2 | 2 | Material handler informs to supervisor about the missing parts. A special transport from supplier is done (safety stock) | Mr. Müller. Tel. 176 879 3333 müller@example.com
3 | Quality problems in production | 1 | 2 | 2 | Inform supervisor in order to ask for temporarily approvals if possible. | Mr. Müller. Tel. 176 879 3333 müller@example.com
4 | Rejected parts in final lines of production | 1 | 3 | 3 | Receiving inspection makes rework temporarily in order to not stop production | Mr. Müller. Tel. 176 879 3333 müller@example.com
5 | Lack of skilled labor willing to relocate | 2 | 2 | 4 | Combination of incentives and benefits of the job rotation program | Mr. Müller. Tel. 176 879 3333 müller@example.com
6 | Labor shortages | 2 | 3 | 6 | See HR Program about potential interns to be hired | Mr. Blanc Tel. 176 879 2222 blanc@example.com
7 | .. | .. | .. | .. | .. | ..
Probability (Likelihood)
|  | 1 | 2 | 3
Impact (Consequence) | 1 | LOW 1 | LOW 2 | MEDIUM 3
| 2 | LOW 2 | MEDIUM 4 | HIGH 6
| 3 | MEDIUM 3 | HIGH 6 | HIGH 9

## 7 Inspection report
Inspection Report
Customer
Supplier
Test performed according: | VDA Norm
Reson for the test: |  | Initial Inspection
Change request
Other
Drawing
Part Number
Material
Order ID
Process
Machine ID
Inspection date
Part Characteristics |  |  |  |  | Inspection / Test Result |  |  |  | Other
ID | Qty | Feature | Requirement (in mm) | Tolerance (in mm) | Result | Correct / Incorrect | Measurement Tool Type | Measurement Tool ID | Notes
B.1 | 1 | Diameter | 4.5 | ± 0,5 | 4.8 |  | Gage Pin | MT 532
B.2 | 1 | Diameter | 5.5 | ± 0,5 | 5.5 |  | Gage Pin | MT 007
…
…
…
Peformed by
Date
Siganture
4,5 ± 0,5
5,5 ± 0,5
B.1
B.2

## 8 Competency Matrix
Competency matrix
Knowledge/competence |  | Process A |  | Process B |  | Product a |  | Product b |  | Process C |  | Process D |  | Product c |  | Product d
Employee |  | target | actual | target | actual | target | actual | target | actual | target | actual | target | actual | target | actual | target | actual
Employee 1
Employee 2 |  | 2021-10-01 |  | 2021-11-01 |  | 2021-12-01 |  |  |  | 2022-02-01 |  | 2022-01-01 |  | 2021-12-01
Employee 3 | [5 empty] | 2022-01-01 | [7 empty] | 2021-11-01
Employee 4
Employee 4
…
…
… Expert
… general knowledge
… no knowledge
… not necessary

## 9 Documented information
Chapter | Description | Example | Create/Approve | Identification | Distribution | Filing | Retention period
4.4.2 | quality management system and its processes
5.3.1 | Organizational roles, responsibilities and authorities - supplemental | list of process owners | quality manager/ site general manager | issue date | management team | issue date | 10 years
6.1.3 | actions to address risks and opportunities - supplemental | risk register | process owner/ site general manager | issue date | management team | issue date | 11 years
7.1.1.1 | resources - general - supplemental
7.1.5.1 | monitoring and measuring resources - general | gauge capability | quality assurance/ quality manager | consecutive number | quality planning | consecutive number | -
7.1.5.2 | measurement traceability | assessment of previous measurements | quality assurance/ engineering | consecutive number | quality department | consecutive number | 20 years
7.1.5.3 | monitoring and measuring resources - supplemental | register of monitoring and measuring equipment | quality assurance | consecutive number | quality department | consecutive number | 20 years
7.2 | competence | competence matrix | team lead | staff number | - | staff number | 5 years
7.2.1 | competence - supplemental
7.5.3.2 | control of documented information
7.5.3.3 | control of documented information - supplemental
8.1.1 | planning for the outsourcing or transfer of processes | transfer plan | project manager/site general manager | project name and issue date | project team, management team | project name and issue date | 10 years
8.1.2 | tender management
8.1.3 | project management
8.1.3.8 | project risk and opportunity management | risk and opportunity register | project manager/ project director | issue date | project team, management team | issue date | 20 years
8.1.4 | configuration management
8.1.5 | change management
8.2.2
8.2.3.2 | review of requirements related to products and services
8.3.2.1
8.3.3 | design and development inputs
8.3.3.1 | design and development inputs - supplemental
8.3.4 | design and development controls
8.3.4.2 | design reviews
8.3.4.3 | design verification
8.3.4.4 | design validation
8.3.5 | design and development outputs
8.3.6 | design and development changes
8.4.1 | control of externally provided processes, products and services
8.4.1.1 | control of externally provided processes, products and services - general - supplemental
8.4.1.1.1 | classification of external providers and external provided products, process or service
8.4.1.1.2 | evaluation of external providers
8.4.1.1.3 | approval of external providers
8.4.1.1.4 | external provider offer selection
8.4.2.1 | external provided products, process or service approval of release | first article inspection report | supplier quality assuranace | item no./date | supplier, customer | item no./date | 20 years
8.4.2.2 | external provided products, process or service verification after release
8.4.2.3 | monitoring of external provider performance, re-evaluation and ranking | annual supplier evaluation | procurement manager/ site general manager | supplier/year | supplier | supplier/year | 10 years
8.4.4 | supply chain management
8.5.1.2 | special processes
8.5.1.3 | production equipment
8.5.2 | identification and traceability
8.5.3 | property belonging to customers or external providers
8.5.6 | control of changes
8.6 | release of products and services
8.7
8.7.2 | control of nonconforming output
8.8 | RAMS/LCC
8.9 | First article inspection
9.1.1 | monitoring, measurement, analysis and evaluation - general
9.2.2 | internal audit | audit planning | quality manager/ site general manager | issue date | processes/departments to be audited | issue date | 10 years
9.2.3 | internal audit - supplemental | competency list of the internal auditors | quality manager/ site general manager | issue date | - | issue date | -
9.3.1.1 | management review - general - supplemental
9.3.3 | management review outputs | management review report | quality manager/ site general manager | calendar year | management team | calendar year | 20 years
10.2 | nonconformity and corrective action
10.2.3 | nonconformity and corrective action - supplemental

## 10 Transfer plan
Transfer Plan
System / Equipment : |  | Part number and index :
New manufacturer unit/supplier (NM) :
Nr. | Items | Required |  | Conform |  | Starting date | End | Responsible | Remark
|  | Yes | No | Yes | No |  | date
Transfer management
1 | Feasibilty study | X
2 | Customer autorisation | X
3 | Audit before transfer done at Bombardier | X
4 | Bombardier autorisation | X
5 | Detailed planning of the transfer process | X
6 | Open issue list at Bombardier available | X
7 | Modifications issued throughout transfer listed | X
8 | Pending non-conformities listed | X
9 | Configuration management available | X
Preparation management
10 | Manufacturing equipment available at NM | X
11 | Components and tools needed for manufacturing are available | X
12 | Technical documents needed for manufacturing available and if necessary translated at NM | X
13 | Industrial documents needed for manufacturing available and if necessary translated at NM | X
14 | Quality documents needed for manufacturing available and if necessary translated at NM | X
15 | Open issue list at NM started | X
16 | New suppliers file validated | X
17 | Purchasing modifications mastered (suppliers, incoming, ..) | X
18 | Logistic modifications mastered (delivery, packaging,schedule, ...) | X
19 | Contingency stock defined and achieved | X
Process management
20 | NM workers trained and qualified on new products or processes | X
21 | Special processes are transfered (welding, painting, crimping, heat treatment, …) | X
22 | Training on special process done | X
23 | Special processes are mastered and qualified | X
24 | First equipment manufactured at NM | X
25 | Type test to performed according list of tests | X
Supplier validation
26 | FAI at NM carried out by Bombardier | X
27 | Audit to the NM processes carried out by Bombardier | X
28 | Corrective Actions Plan (to FAI / audit of Bombardier) sent by NM to Bombardier | X
29 | Corrective actions derived from FAI / audit done by Bombardier are under control | X
30 | Authorisation for Manufacturing of series sent by Bombardier | X
Customer validation
31 | FAI at NM carried out by customer | X
32 | Audit to the NM processes carried out by customer | X
33 | Corrective Actions Plan (to FAI / audit of Client) sent by NM to customer and Bombardier | X
34 | Corrective actions derived from FAI / audit done by customer are under control | X
35 | Authorisation for manufacturing of series sent by customer | X
Reliability evidences
36 | Incoming inspection level at Bombardier adapted to NM product quality level | X
37 | Q & D product performance checked in NM (no recurrent non-conformity) | X
|  | Written by | Verified by |  |  |  | Customer approval (when applicable)
| Position |  |  | Company
| Name |  |  | Name
| Date |  |  | Date
| Signature |  |  | Signature

## 11 Change Management Register
Change Management Register
|  |  |  | Application to departments teams | [6 empty] | Implementation and date
Change request | [5 empty] | Production | [6 empty] | Production |  |  | Suppliers
CR number | CR topic | CR number of customer | Date | R&D | EN | Tools | Areas | Documents, drawings, inspection plan | Suppliers | Logistics | R&D | EN | Tools | Areas | Documents, drawings, inspection plan | Batch Nr. of first product | Logistic
2021-001 | Change of material XY to material XZ DWG 789-546 | - | 2021-02-01 |  | X |  |  | X |  |  |  | 2021-02-05 |  |  | 2021-02-05 | CN753
2021-002
2021-003

## 12 Requirements matrix
Requirements traceability matrix
Project name: |  |  |  |  | ABC |  |  | Project number: | 12345
Project manager: |  |  |  |  | Mr. XY |  |  | Status: | 2021-02-08
ID | Requirements cluster | Object type | Headline | Requirement original | Requirement (translation of the customer requirements into design / technical requirements) | Evaluation | Comment | Responsible | Status | Influence on req. ID | Solution | Technical Speification | System / Component
1 | Technical | Heading | 1. Painting |  |  | compliant | Compliant with a different solution | Mr. XY
2 | Technical | Requirement | 1.1 Corrosion resistance | corrosion resistance for 25 years |  | compliant |  | Mr. XY | closed | #1 | Paint XY, layer thickness x µm, pre-treatment: degreasing & sandblasting | Painting specification | Component YX
3 | Technical | Information |  |  |  | non compliant |  | Mr. XY | open
4 | Commercial | Information | Penalties | In case of not fulfilling the delivery schedule a penalty of XX is due. |  |  |  | Mr. XY |  | #13
5 | Quality | Requirement | 2. Identification | Components XY have to be identified by a unique identification code |  | compliant with risk |  | Mr. XY |  |  | Use of serialization wiht unique QR code
6 | Quality | Requirement | 3. Testing | Rubber metal parts need to fulfill requirements regarding hysteresis as defined in specification XXX |  | compliant |  | Mr. XY |  |  |  | Specification XXX
7 | Quality | Requirement | 4. Documentation | all 3.1 certificates must be handed over electronically |  | compliant |  | Mr. XY
8 | Environmental, health & safety | [6 empty] | Mr. XY
9 | legal | [6 empty] | Mr. XY
10 | homologation | [6 empty] | Mr. XY
11 | Management | Requirement | 5. Deliveries | Deliveries need be be in accordance to delivery plan |  | compliant |  | Mr. XY | closed |  | Delivery plan is alligned with production capacity, material avaiability etc.
12 | … | … | … | … | … | … | … | … | … | … | … | … | …

## 16 Supplier Fact Sheet
Supplier Fact Sheet
| Supplier Name: | Max Mustermann GmbH |  |  | Portfolio: |  |  |  |  | Status: |  | Approved/ Rejected
| Supplier number: | 1234 |  |  | Alternate Suppliers: |  |  |  |  | Classification: |  | A, B or C
QM-Systems / Standards:
| Standard: | ISO 9001:2015 | IRIS
| Valid until: | 2022-10-01 | 2022-10-01
Technical Qualifications / Special processes / Delegated verifications:
|  | Welding | Paint | Glueing | … | …
Standard:
Valid until:
Performance:
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
| KPIs | Year. Month | 2021-01-01 | 2021-02-01 | Mar-21 | 2021-04-01 | May-21 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | Oct-21 | 2021-11-01
| On Time Delivery | Actual | 80% | 81% | 75% | 60% | 50% | 60% | 70% | 80% | 40% | 60% | 65%
|  | YTD | 80% | 81% | 79% | 74% | 69% | 68% | 68% | 70% | 66% | 66% | 66%
|  | Target | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75%
| Complaint Rate | Actual | 1.5% | 0.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 0%
|  | YTD | 1.5% | 1% | 0.67% | 0.5% | 0.4% | 0.33% | 0.29% | 0.25% | 0.22% | 0.7% | 0.64%
Target | bar: 1 to 11
| Quality Deficiency costs | Actual | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 110
|  | YTD | 10 | 30 | 60 | 100 | 150 | 210 | 280 | 360 | 450 | 550 | 660
|  | Target | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000
| QDC/Revenue | Actual [%] | 1.2% | 1.8% | 2.5% | 1.4% | 2.1% | 3.4% | 1% | 2.3% | 2.7% | 1.9% | 1.6%
|  | YTD [%] | 1.2% | 1.5% | 1.8% | 1.7% | 1.8% | 2.1% | 1.9% | 2% | 2% | 2% | 2%
Target [%] | bar: 1 to 11

## Table 3 Production readiness
Topic | Responsible | yes | no | Remarks
Are there development requirements for production available and clear? (product specification, test specification, labelling, traceability etc.) | Development/Construction
Has the hardware design been approved? | Development/Construction
Has the product master data been created (item number, version etc.)? | Development/Construction
Is there approved production data (parts lists, hardware data, software data, drawings, etc.) available? | Development/Construction
Has the First Article Inspection of the procurement items been successfully passed? | Quality Assurance
Is the required material available in sufficient quantity? | Procurement
Are storage quantities and restocking time fixed with suppliers? | Procurement
Are approved inspection scopes as well as inspection plans for the incoming goods inspection available? | Quality Assurance
Are the necessary storage capacities available? | Warehouse
Has the product and production process FMEA been completed? | Quality Assurance
Are the required workplaces, machines, equipment, devices available? | Production Planning
Are approved machine programmes available? | Production Planning
Has the capability of machines and devices been demonstrated? | Production Planning
Are maintenance plans and maintenance instructions in place? | Maintenance
Is the manufacturing instruction available? | Production Planning
Are the process specifications for special processes ready? | Production Planning
Do the employees have the necessary competence to manufacture the product? | Production Planning
Is a sufficient initial production quantity defined to demonstrate process capability? | Production Planning
Is a capable testing device available and has it been approved? | Production Planning
Is there an approved test scope and test procedure? | Production Planning
Are plans and instructions for the monitoring of test equipment available? | Maintenance
Has the product packaging been defined and is it available? | Warehouse / Logistics
Has a production order been scheduled? | Production Planning

## 18 MQCP
Manufacturing Quality Control Plan
Quality Control Plan Number: |  | ABC 001 |  |  | Product Number: | 12345 | Product Name: |  | XY |  |  | Contact: | Mr. XY
Document Revision: |  | A1 |  |  | Release Date: | 2021-02-08 | Status: |  | Serial Production
Process Step | Process Name | No. | Characterisric | Technique | Reference Documents / Drawings | Specification / Nominal | Measuring unit | Upper Tolerance | Lower Tolerance | Evaluation / Measurement Equipment | Quantity | Frequency | Control Method | Reaction Plan | Test record
1 | Process 1 | 1 | Surface | visual | DWG 123 | without visible burr and stains | N/A |  |  |  | 10% | per lot | Sampling | Rework / Scrap | Record 123
|  | 2 | Length XY | measure | DWG 123 | 11.5 | cm | 11.1 | 11.9 | Vernier caliper | 5% | per lot | Sampling | Rework / Scrap | Record 123
|  | 3 | [12 empty] | Record 123
|  | 4 | Tensile | destructive | ISO 6892, DWG 123 | RM | N/mm² |  |  | Tensile testing maschine XY |  |  | Sampling | Scrap | Record 123
2 | Process 2 | 1 | Lengh YZ | measure | DWG 456 |  | cm |  |  | CMM 12, Programm XYZ |  |  |  |  | Record 234
|  | 2 |  | measure | [9 empty] | Return to supplier | Record 234
|  | 3 | [12 empty] | Record 234
3 | Process 3 | 1 | XY | function | SPEC 123 |  | N/A |  |  |  | 100% | per lot | Full check | Rework
2
3
4
5

## 19 FAI
First Article Inspection
Document Nr.
| FAI Typ |  | Product 1
Product 2
Product 3
| FAI Reason |  | New Supplier |  |  |  | Change production sequence
|  |  | Changed Design |  |  |  | Production Interruption
|  |  | Repeated Inspection |  |  |  | New or Changed Part
|  |  | New Manufacturing facility |  |  |  | Other
| Participants | Name |  | Signature |  | Name |  | Signature
| Serial Production |  |  | Released
Released with condition
Blocked
Confirmation
| We declare that: | 1. The shown samples were produces with serial tools and under serial conditions
2. The FAI and description in this report were made correctly in all conscience, deviations were registered and resolved before delivery
|  | Date |  |  | Name |  |  |  | Signature
Responsible 1
Responsible 2
Responsible 3
Responsible 4
Reviewed material / system / component
| Article Number | ID | Drawing and description |  | Revision | Quantity |  | Serial number | Manufacturing date
…
…
Co-applicable Documens
| Identification Nr. | Document |  |  | Drawing |  | Date | Comments
| FAI Performed by | [5 empty] | Created by
| Date | [5 empty] | Checked by
| Signature | [5 empty] | Approved by
Revision
Date
Distribution list

## 20 Audit Plan
Audit Plan
Register # | functions involved | General Management | Site Engineering | Bids | Human Resources | Procurement | Project Management | Welding | Production Control | Production | Service | Wheelset Center | Technical Services | Continous Improvement | Site Quality | Controlling | Warrenty | Type of audit | Planned audit date | Lead auditor | Co-Auditor | Remarks
business processes
1 | Management Responsibility | X | [15 empty] | SA
4.1, 4.2, 4.3, 4.4, 5.1, 5.2, 5.3, 6.1, 6.2, 6.3, 6.4, 7.4, 8.6, 8.7, 9, 10
2 | Design and development |  | X | [14 empty] | SA
7.5, 7.1.6, 6,7.2, 7.3, 8.1.3, 8.1.4, 8.1.5, 8.2, 8.3, 8.8, 8.9, 8.10
3 | Tender Management |  |  | X | [13 empty] | SA
5.1.2, 6.2, 7.5.2, 7.5.3, 7.1.6, 8.1.3, 8.1.4, 8.1.5, 8.2, 8.7, 8.8, 8.10, 8.11, 9.1.1, 9.1.2, 10.1, 10.3
4 | Human Resources |  |  |  | X | [12 empty] | SA
7.1, 7.2, 7.3, 7.5, 10.1, 10.3
5 | Warranty | [15 empty] | X | SA
7.5.2, 7.5.3
6 | Controlling | [14 empty] | X |  | SA
7.5.2, 7.5.3, 9.1.1, 9.1.3, 10.1, 10.3
7 | Purchasing |  |  |  |  | X | [11 empty] | SA
6.1.4, 7.1.6, 7.5.2, 7.5.3, 8.4, 8.6, 8.7, 8.9, 8.10, 9.1.1, 10.1, 10.3
8 | Project Management | [5 empty] | X | [10 empty] | SA
6, 7.1, 7.1.6, 7.5.2, 7.5.3, 8.1, 8.5, 8.7, 8.8, 8.9, 8.10, 9.1.1, 9.1.3, 10
9 | Welding | [6 empty] | X | [9 empty] | SA
6.1.4, 7.1.6, 7.2, 7.5.2, 7.5.3, 8.4, 8.5.1, 8.5.5, 8.7, 9.1.1, 10.1, 10.3
10 | Production Control | [7 empty] | X | [8 empty] | SA
7.5.2, 7.5.3, 7.1.1, 7.1.2, 8.5, 8.5.1, 8.5.5, 8.6, 8.7, 10.1, 10.3
11 | Production | [8 empty] | X | [7 empty] | SA |  |  |  | All shifts
4, 7.1.3, 7.1.5, 7.2, 8.5, 8.6, 8.7, 8.9, 9.1.1, 10.1, 10.3
12 | Maintenance - Production | [9 empty] | X | [6 empty] | SA |  |  |  | All shifts
5.1.2, 6, 7.1.6, 7.5.2, 7.5.3, 8.1.3, 8.1.5, 8.2, 8.5, 8.4, 8.5, 10.1, 10.3
13 | Maintenance - Project Management | [9 empty] | X | [6 empty] | SA
6, 7.1, 7.1.6, 7.5.2, 7.5.3, 8.1, 8.5, 8.7, 8.8, 8.9, 8.10, 9.1.1, 9.1.3, 10
14 | Purchasing | [9 empty] | X | [6 empty] | SA
6.1.4, 7.1.6, 7.5.2, 7.5.3, 8.4, 8.6, 8.7, 8.9, 8.10, 9.1.1, 10.1, 10.3
15 | Wheelset Center | [10 empty] | X | [5 empty] | SA
4, 7.1.3, 7.1.5, 7.2, 8.5, 8.6, 8.7, 8.9, 9.1.1, 10.1, 10.3
16 | Technical Services | [11 empty] | X |  |  |  |  | SA
4, 7.2, 7.1.3, 7.1.4, 6.1.4, 8.5.1, 8.5.5, 7.1.5, 10.1, 10.3
17 | Quality | [13 empty] | X |  |  | SA
8.5.1, 8.5.5, 8.9, 9.2, 8.6, 8.7, 10
18 | Welding |  |  |  | X | [12 empty] | PzA
6.1.4, 7.1.6, 7.2, 7.5.2, 7.5.3, 8.4, 8.5.1, 8.5.5, 8.7, 9.1.1, 10.1, 10.3
19 | Project A | [5 empty] | X | [10 empty] | ProjA
20 | Project B | [6 empty] | X | [9 empty] | ProjA
21 | Product 1 | [7 empty] | X | [8 empty] | ProdA
22 | Product 2 | [10 empty] | X | [5 empty] | ProdA
23
|  |  | Date / signature | [14 empty] | Legend
[18 empty] | SA | system audit
| Created: Quality manager | [16 empty] | PzA | process audit
[18 empty] | ProdA | product audit
| Approved: Site general manager | [16 empty] | ProjA | project audit

## 21 Process Review Report
[8 empty] | KPI 1 | On time delivery |  | KPI 2 | Non Conformities raised by the customer
[9 empty] | Actual | Target |  | Actual | Target
PROCESS REVIEW REPORT | [7 empty] | Jan | 98% | 98% | Jan | 1% | 1%
[8 empty] | Feb | 95% | 98% | Feb | 0.5% | 1%
* mandatory information |  |  |  | Report ID: |  |  |  | Mrz | 96% | 98% | Mrz | 0.6% | 1%
[8 empty] | Apr | 97% | 98% | Apr | 0.8% | 1%
PROCESS DATA | [7 empty] | Mai | 92% | 98% | Mai | 1.2% | 1%
Process name* | [7 empty] | Jun | 95% | 98% | Jun | 1.5% | 1%
Process Owner* | [7 empty] | Jul | 93% | 98% | Jul | 0.6% | 1%
Top management representative(s)* | [7 empty] | Aug | 98% | 98% | Aug | 0.8% | 1%
[8 empty] | Sep | 99% | 98% | Sep | 0.9% | 1%
[8 empty] | Okt | 91% | 98% | Okt | 1% | 1%
Relevant Process description (e.g. Turtle)* |  | Document ID |  | Name |  | Rev | Status | Nov | 95% | 98% | Nov | 1.1% | 1%
[7 empty] | < please choose > | Dez | 96% | 98% | Dez | 2.1% | 1%
Relevant Process Documents (optinal) |  | Document ID |  | Name |  | Rev | Status
< please choose >
< please choose >
< please choose >
REVIEW DATA (review at least every 12 month)*
Date of this Review |  |  |  | Date of last Review
PARTICIPANTS (relevant stakeholder) |  | Stakeholder (function) |  | Name of stakeholder representative |  |  | Signature
PERFORMANCE MEASUREMENT
No. | Definition of KPI | Target value |  | Actual value | Trend |  | Comments
PERFORMANCE EVALUATION | [6 empty] | (mark with X)
PROCESS APPLICATION (DEPLOYMENT) | D1 The process is documented, established, implemented and maintained. However the process is NOT delivering the CUSTOMER EXPECTED PERFORMANCE and appropriate action is NOT being taken. |  | B1 The process is documented, established, implemented and maintained. However the process is NOT delivering the CUSTOMER EXPECTED PERFORMANCE but appropriate action is being taken. |  |  | A The process is documented, established, implemented and maintained. Furthermore the process is delivering the CUSTOMER EXPECTED PERFORMANCE and there are no nonconformities identified.
| D3 The process is documented, established, partially implemented and therefore partially maintained. However the process is NOT delivering the CUSTOMER EXPECTED PERFORMANCE and appropriate action is NOT being taken. |  | C The process is documented, established, partially implemented and therefore partially maintained. However the process is NOT delivering the CUSTOMER EXPECTED PERFORMANCE but appropriate action is being taken. |  |  | B2 The process is documented, established, partially implemented and therefore partially maintained. However the process is delivering the CUSTOMER EXPECTED PERFORMANCE.
| E The process is NOT documented, established, implemented and maintained. Furthermore the process is NOT delivering the CUSTOMER EXPECTED PERFORMANCE and appropriate action is NOT being taken. |  | D4 The process is NOT documented, established, implemented and maintained. However the process is NOT delivering the CUSTOMER EXPECTED PERFORMANCE but appropriate action is being taken. |  |  | D2 The process is NOT documented, established, implemented and maintained. However the process is delivering the CUSTOMER EXPECTED PERFORMANCE.
PROCESS PERFORMANCE
Justification
ACTIONS
| Actions from previous review reviewed* |  |  | Add open actions from last review to the new action log.
| Ressources are available and effective* |  |  | Processes need to be updated
A/D | Outcome: Actions/Decision* |  | To be reported in management review | Responsible |  |  | Due Date
| Location, Date |  |  | Signature of Process Operator

## FMEA
FMEA Worksheet
Type of FMEA | Process | [10 empty] | Submitted by
FMEA Number | TOR001 | [10 empty] | Date
Team | 1.
2.
3.
4.
5.
[5 empty] | Current state | [6 empty] | Improved state
Process | ID | Potential Failure Mode | Potential Failure Effect | Potential Failure Cause | Means of Control | O* | S* | D* | RPN* | Recommended Action | Responsible & Target Date | Measures taken | O* | S* | D* | RPN*
Torque | T1.1 | Screw not fully seated | Defective parts | Nut runner not perpendicular to work surface | Angle sensor incuded | 6 | 6 | 4 | 144
| T1.2 | Screw torqued too high | Rework at the end of stations | Torque setting set too high by ,set-up personnel´ | Training of set up personnel | 5 | 6 | 6 | 180 | Torque validation test | Mr. Müller. 01.05.2021
| T1.3 | Screw torqued too low | Rework at the end of stations | Torque setting set too low by ,set-up personnel´ | Visual aid with screw specifications | 5 | 6 | 6 | 180 | Torque validation test | Mr. Müller. 01.02.2021
| T1.4 | Wrong screw used | Wrong assembly of part | Similar screws availables | Visual aid with screw specifications | 8 | 6 | 6 | 288 | Visual Inspection in station | Mr. Müller. 01.06.2021
| T1.5 | Screw placed in wrong holes | Rework in next stations | Amount of available holes to operator | Visual aid identifying location of screws | 7 | 6 | 6 | 252
O* - Occurence
Probability of occurrence of failure cause
extremly unlikely = 1
remote = 2 - 3
occasional = 4 - 6
reasonably = 7 - 8
frequent = 9 -10
S* - Significance (or severity)
Consequences of a failure effect for the customer
no relevant effect = 1
minor damage = 2 - 3
moderate damage = 4 - 6
critical = 7 - 8
catastrophic = 9 -10
D* - Detection
Probablility that the failure cause is detected
(Before delivery to customer)
certain = 1
almost certain = 2 - 3
moderate = 4 - 6
low = 7 - 8
failure is undetected = 9 -10
RPN* - Risk Priority Number
high <= 1000
moderate <= 250
low <= 125
none = 1